## Fernão Dias
* Valores atualizados até dezembro de 2013
ITEM DO PER | DESCRIÇÃO | Km Inicial | Km Final | Projeto Executivo | Licenciamento ambiental | Proposta de Declaração de Utilidade Pública | CRONOGRAMA PROPOSTO OU EXECUTADO |  |  | % Realizado até o 5º ano |  | 6º ANO | [11 empty] | 7º ANO | [24 empty] | % acumulado
|  |  |  | SITUAÇÃO ATUAL | SITUAÇÃO | SITUAÇÃO | DATA DE INÍCIO (dd/mm/aaaa) | DATA DE CONCLUSÃO (dd/mm/aaaa) | Duração da Obra (dias) |  |  | MAR | ABR | MAI | JUN | JUL | AGO | SET | OUT | NOV | DEZ | JAN | FEV | MAR | ABR | MAI | JUN | JUL | AGO | SET | OUT | NOV | DEZ | JAN | FEV | MAR | ABR | MAI | JUN | JUL | AGO | SET | OUT | NOV | DEZ | JAN | FEV | MAR | % Previsto e Executado no TAC |  | Situação | % total executado
5.1.2. Execução de Variantes e Contornos (inclusive OAE's) | Conclusão do Contorno de Betim - L = 5,38 km (2ª Etapa) - Trevo Bandeirinhas / Trevo da Krup |  |  | APROVADO | LICENCIADA | PUBLICADO | 2011-09-22 | 2013-09-30 | 739 | 49% | PREVISTO | 6º ANO MAR: 3.5%; 6º ANO ABR: 7.5%; 6º ANO MAI: 4%; 6º ANO JUN: 7%; 6º ANO JUL: 8%; 6º ANO AGO: 5%; 6º ANO SET: 16% | PREVISTO | 16% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAR: 3.5%; 6º ANO ABR: 7.5%; 6º ANO MAI: 4%; 6º ANO JUN: 7%; 6º ANO JUL: 8%; 6º ANO AGO: 5%; 6º ANO SET: 15%; 6º ANO OUT: 1%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 16%
5.1.3.1. Execução de Ruas Laterais em Pista Simples (94,26 km) | km 480,103 ao km 480,554 - Pista Norte - Contagem/MG - 0,451 km (correspondente ao km 480,100 ao km 480,500 - Pista Norte - Contagem/MG - 0,400 km) | 480.103 | 480.554 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-05-09 | 2013-10-06 | 150 | 0% | PREVISTO | 6º ANO MAI: 15%; 6º ANO JUN: 45%; 6º ANO JUL: 4%; 6º ANO AGO: 8%; 6º ANO SET: 10%; 6º ANO OUT: 18% | PREVISTO | 28% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAI: 15%; 6º ANO JUN: 45%; 6º ANO JUL: 4%; 6º ANO AGO: 8%; 6º ANO SET: 17%; 6º ANO OUT: 11%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 28%
| km 480,610 ao km 481,132 - Pista Norte - Contagem/MG - 0,522 km (correspondente ao km 480,600 ao km 481,000 - Pista Norte - Contagem/MG - 0,400 km) | 480.61 | 481.132 | APROVADO | LICENCIADA | NÃO SE APLICA | 2012-10-23 | 2013-09-11 | 323 | 12% | PREVISTO | 6º ANO MAR: 1e-13%; 6º ANO ABR: 47%; 6º ANO MAI: 21%; 6º ANO JUN: 1e-13%; 6º ANO JUL: 15%; 6º ANO AGO: 2%; 6º ANO SET: 3% | PREVISTO | 3% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAR: 1e-13%; 6º ANO ABR: 47%; 6º ANO MAI: 21%; 6º ANO JUN: 1e-13%; 6º ANO JUL: 15%; 6º ANO AGO: 2%; 6º ANO SET: 3%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 3%
| km 481,475 ao km 481,936 - Pista Norte - Contagem/MG - 0,461 km (correspondente ao km 481,600 ao km 482,000 - Pista Norte - Contagem/MG - 0,400 km) | 481.475 | 481.936 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-04-09 | 2013-10-31 | 205 | 0% | PREVISTO | 6º ANO ABR: 6%; 6º ANO MAI: 24%; 6º ANO JUN: 12%; 6º ANO JUL: 28%; 6º ANO AGO: 8%; 6º ANO SET: 10%; 6º ANO OUT: 12% | PREVISTO | 22% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO ABR: 6%; 6º ANO MAI: 24%; 6º ANO JUN: 12%; 6º ANO JUL: 28%; 6º ANO AGO: 8%; 6º ANO SET: 4%; 6º ANO OUT: 9%; 6º ANO NOV: 2%; 6º ANO DEZ: 2%; 6º ANO JAN: 4%; 6º ANO FEV: 1%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 22%
| km 485,660 ao km 486,254 - Pista Sul - Betim/MG - 0,594 km (correspondente ao km 485,600 ao km 486,215 - Pista Sul - Betim/MG - 0,615 km) | 485.66 | 486.254 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-15 | 2013-12-12 | 150 | 0% | PREVISTO | 6º ANO JUL: 15%; 6º ANO AGO: 35%; 6º ANO SET: 6%; 6º ANO OUT: 10%; 6º ANO NOV: 15%; 6º ANO DEZ: 19% | PREVISTO | 50% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 15%; 6º ANO AGO: 35%; 6º ANO SET: 7%; 6º ANO OUT: 3%; 6º ANO NOV: 0%; 6º ANO DEZ: 4%; 6º ANO JAN: 2%; 6º ANO FEV: 17%; 7º ANO MAR: 4%; 7º ANO ABR: 2%; 7º ANO MAI: 10%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 1%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 50%
| km 485,442 ao km 486,040 - Pista Norte - Betim/MG - 0,598 km (correspondente ao km 485,600 ao km 486,000 - Pista Norte - Betim/MG - 0,400 km) | 485.442 | 486.04 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-11 | 2013-12-08 | 150 | 0% | PREVISTO | 6º ANO JUL: 11%; 6º ANO AGO: 8%; 6º ANO SET: 11%; 6º ANO OUT: 18%; 6º ANO NOV: 24%; 6º ANO DEZ: 28% | PREVISTO | 81% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 11%; 6º ANO AGO: 8%; 6º ANO SET: 21%; 6º ANO OUT: 5%; 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 3%; 6º ANO FEV: 13%; 7º ANO MAR: 3%; 7º ANO ABR: 13%; 7º ANO MAI: 5%; 7º ANO JUN: 0%; 7º ANO JUL: 2%; 7º ANO AGO: 6%; 7º ANO SET: 9%; 7º ANO OUT: 1%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 81%
| km 487,327 ao km 488,207 - Pista Sul - Betim/MG - 0,880 km (correspondente ao km 487,300 ao km 488,200 - Pista Sul - Betim/MG - 0,900 km) | 487.327 | 488.207 | APROVADO | LICENCIADA | PUBLICADO (25/02/2015) | 2014-01-26 | 2014-06-25 | 150 | 0% | PREVISTO | 6º ANO JAN: 6%; 6º ANO FEV: 12%; 7º ANO MAR: 17%; 7º ANO ABR: 17%; 7º ANO MAI: 25%; 7º ANO JUN: 23% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 10%; 6º ANO OUT: 1%; 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 21%; 7º ANO JUL: 11%; 7º ANO AGO: 7%; 7º ANO SET: 23%; 7º ANO OUT: 4%; 7º ANO NOV: 9%; 7º ANO DEZ: 12%; 7º ANO JAN: 2%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 488,400 ao km 489,325 - Pista Norte - Betim/MG - 0,925 km (correspondente ao km 489,000 ao km 489,300 - Pista Norte - Betim/MG - 0,300 km) | 488.4 | 489.325 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-05-09 | 2013-11-05 | 180 | 0% | PREVISTO | 6º ANO MAI: 20%; 6º ANO JUN: 2%; 6º ANO JUL: 18%; 6º ANO AGO: 6%; 6º ANO SET: 15%; 6º ANO OUT: 18%; 6º ANO NOV: 21% | PREVISTO | 54% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAI: 20%; 6º ANO JUN: 2%; 6º ANO JUL: 18%; 6º ANO AGO: 6%; 6º ANO SET: 11%; 6º ANO OUT: 12%; 6º ANO NOV: 7%; 6º ANO DEZ: 2%; 6º ANO JAN: 18%; 6º ANO FEV: 4%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 54%
| km 489,695 ao km 490,105 - Pista Sul - Betim/MG - 0,410 km (correspondente ao km 489,550 ao km 489,900 - Pista Sul - Betim/MG - 0,350 km) | 489.695 | 490.105 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-05-02 | 2013-11-30 | 212 | 0% | PREVISTO | 6º ANO MAI: 20%; 6º ANO JUN: 10%; 6º ANO JUL: 13%; 6º ANO AGO: 15%; 6º ANO SET: 8%; 6º ANO OUT: 13%; 6º ANO NOV: 21% | PREVISTO | 42% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAI: 20%; 6º ANO JUN: 10%; 6º ANO JUL: 13%; 6º ANO AGO: 15%; 6º ANO SET: 22%; 6º ANO OUT: 17%; 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 3%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 42%
| km 489,692 ao km 490,753 - Pista Norte - Betim/MG - 1,061 km (correspondente ao km 489,700 ao km 490,780 - Pista Norte - Betim/MG - 1,080 km) | 489.692 | 490.753 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-08-06 | 2014-01-31 | 178 | 0% | PREVISTO | 6º ANO AGO: 4%; 6º ANO SET: 8%; 6º ANO OUT: 12%; 6º ANO NOV: 20%; 6º ANO DEZ: 25%; 6º ANO JAN: 31% | PREVISTO | 96% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 4%; 6º ANO SET: 14%; 6º ANO OUT: 11%; 6º ANO NOV: 6%; 6º ANO DEZ: 2%; 6º ANO JAN: 0%; 6º ANO FEV: 5%; 7º ANO MAR: 5%; 7º ANO ABR: 2%; 7º ANO MAI: 14%; 7º ANO JUN: 6%; 7º ANO JUL: 13%; 7º ANO AGO: 6%; 7º ANO SET: 8%; 7º ANO OUT: 3%; 7º ANO NOV: 0%; 7º ANO DEZ: 1%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 96%
| km 491,400 ao km 491,728 - Pista Sul - Betim/MG - 0,328 km (correspondente ao km 491,400 ao km 491,570 - Pista Sul - Betim/MG - 0,170 km) | 491.4 | 491.728 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-09-03 | 2014-02-28 | 178 | 0% | PREVISTO | 6º ANO SET: 12%; 6º ANO OUT: 17%; 6º ANO NOV: 17%; 6º ANO DEZ: 12%; 6º ANO JAN: 23%; 6º ANO FEV: 19% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 5%; 6º ANO OUT: 3%; 6º ANO NOV: 1%; 6º ANO DEZ: 1%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 1%; 7º ANO AGO: 1%; 7º ANO SET: 16%; 7º ANO OUT: 40%; 7º ANO NOV: 11%; 7º ANO DEZ: 17%; 7º ANO JAN: 4%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 492,660 ao km 493,828- Pista Sul - Betim/MG - 1,168 km (correspondente ao km 492,700 ao km 493,900- Pista Sul - Betim/MG - 1,200 km) | 492.66 | 493.828 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-10-01 | 2014-03-31 | 181 | 0% | PREVISTO | 6º ANO OUT: 12%; 6º ANO NOV: 17%; 6º ANO DEZ: 17%; 6º ANO JAN: 12%; 6º ANO FEV: 23%; 7º ANO MAR: 19% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 3%; 6º ANO OUT: 0%; 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 8%; 7º ANO JUN: 16%; 7º ANO JUL: 8%; 7º ANO AGO: 16%; 7º ANO SET: 32%; 7º ANO OUT: 12%; 7º ANO NOV: 5%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 494,355 ao km 495,120 - Pista Sul - Betim/MG - 0,765 km (correspondente ao km 494,100 ao km 495,250 - Pista Sul - Betim/MG - 1,150 km) | 494.355 | 495.12 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-09-05 | 2014-02-28 | 176 | 0% | PREVISTO | 6º ANO SET: 12%; 6º ANO OUT: 17%; 6º ANO NOV: 17%; 6º ANO DEZ: 12%; 6º ANO JAN: 23%; 6º ANO FEV: 19% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 10%; 6º ANO OUT: 14%; 6º ANO NOV: 2%; 6º ANO DEZ: 11%; 6º ANO JAN: 0%; 6º ANO FEV: 2%; 7º ANO MAR: 3%; 7º ANO ABR: 9%; 7º ANO MAI: 23%; 7º ANO JUN: 7%; 7º ANO JUL: 9%; 7º ANO AGO: 4%; 7º ANO SET: 1%; 7º ANO OUT: 5%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 495,120 ao km 495,490 - Pista Sul - Betim/MG - 0,370 km (correspondente ao km 495,250 ao km 495,590 - Pista Sul - Betim/MG - 0,340 km) | 495.12 | 495.49 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-09-05 | 2014-02-28 | 176 | 0% | PREVISTO | 6º ANO SET: 12%; 6º ANO OUT: 17%; 6º ANO NOV: 17%; 6º ANO DEZ: 12%; 6º ANO JAN: 23%; 6º ANO FEV: 19% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 10%; 6º ANO OUT: 14%; 6º ANO NOV: 0%; 6º ANO DEZ: 4%; 6º ANO JAN: 8%; 6º ANO FEV: 5%; 7º ANO MAR: 21%; 7º ANO ABR: 24%; 7º ANO MAI: 6%; 7º ANO JUN: 5%; 7º ANO JUL: 2%; 7º ANO AGO: 1%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 494,347 ao km 495,247 - Pista Norte - Betim/MG - 0,900 km (correspondente ao km 494,100 ao km 495,100 - Pista Norte - Betim/MG - 1,000 km) | 494.347 | 495.247 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-10-02 | 2014-03-28 | 177 | 0% | PREVISTO | 6º ANO OUT: 12%; 6º ANO NOV: 17%; 6º ANO DEZ: 17%; 6º ANO JAN: 12%; 6º ANO FEV: 23%; 7º ANO MAR: 19% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 7%; 6º ANO OUT: 1%; 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 15%; 7º ANO JUN: 8%; 7º ANO JUL: 16%; 7º ANO AGO: 27%; 7º ANO SET: 10%; 7º ANO OUT: 4%; 7º ANO NOV: 0%; 7º ANO DEZ: 6%; 7º ANO JAN: 6%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 495,902 ao km 496,026 - Pista Sul - Betim/MG - 0,124 km (correspondente ao km 495,800 ao km 496,100 - Pista Sul - Betim/MG - 0,300 km) | 495.902 | 496.026 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-09-01 | 2014-02-28 | 180 | 0% | PREVISTO | 6º ANO AGO: 5%; 6º ANO SET: 6%; 6º ANO OUT: 6%; 6º ANO NOV: 9%; 6º ANO DEZ: 18%; 6º ANO JAN: 25%; 6º ANO FEV: 31% | PREVISTO | 95% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 5%; 6º ANO SET: 49%; 6º ANO OUT: 21%; 6º ANO NOV: 4%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 17%; 7º ANO SET: 4%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 95%
| km 496,000 ao km 496,500 - Pista Norte - Betim/MG - 0,500 km (correspondente ao km 496,000 ao km 496,500 - Pista Norte - Betim/MG - 0,500 km) | 496 | 496.5 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-02-01 | 2014-05-31 | 119 | 0% | PREVISTO | 6º ANO FEV: 8%; 7º ANO MAR: 12%; 7º ANO ABR: 38%; 7º ANO MAI: 42% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO FEV: 18%; 7º ANO MAR: 14%; 7º ANO ABR: 7%; 7º ANO MAI: 9%; 7º ANO JUN: 2%; 7º ANO JUL: 34%; 7º ANO AGO: 5%; 7º ANO SET: 10%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 1%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 496,250 ao km 496,891 - Pista Sul - Betim/MG - 0,641 km (correspondente ao km 496,250 ao km 496,930 - Pista Sul - Betim/MG - 0,680 km) | 496.25 | 496.891 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-02-01 | 2014-05-31 | 119 | 0% | PREVISTO | 6º ANO FEV: 8%; 7º ANO MAR: 12%; 7º ANO ABR: 38%; 7º ANO MAI: 42% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO FEV: 9%; 7º ANO MAR: 9%; 7º ANO ABR: 4%; 7º ANO MAI: 37%; 7º ANO JUN: 18%; 7º ANO JUL: 11%; 7º ANO AGO: 12%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 500,235 ao km 500,862 - Pista Sul - Betim/MG - 0,627 km (correspondente ao km 500,300 ao km 500,700 - Pista Sul - Betim/MG - 0,400 km) | 500.235 | 500.862 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-02-01 | 2014-05-31 | 119 | 0% | PREVISTO | 6º ANO FEV: 8%; 7º ANO MAR: 12%; 7º ANO ABR: 38%; 7º ANO MAI: 42% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO FEV: 9%; 7º ANO MAR: 5%; 7º ANO ABR: 3%; 7º ANO MAI: 34%; 7º ANO JUN: 20%; 7º ANO JUL: 7%; 7º ANO AGO: 2%; 7º ANO SET: 2%; 7º ANO OUT: 2%; 7º ANO NOV: 12%; 7º ANO DEZ: 4%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 504,640 ao km 506,340 - Pista Norte - Betim/MG - 1,700 km (Correspondente ao km 504,900 ao km 506,200 - Pista Norte - Betim/MG - 1,300 km | 504.64 | 506.34 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-08-02 | 2014-02-28 | 210 | 0% | PREVISTO | 6º ANO AGO: 5%; 6º ANO SET: 0%; 6º ANO OUT: 10%; 6º ANO NOV: 14%; 6º ANO DEZ: 25%; 6º ANO JAN: 24%; 6º ANO FEV: 22% | PREVISTO | 95% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 5%; 6º ANO SET: 7%; 6º ANO OUT: 18%; 6º ANO NOV: 4%; 6º ANO DEZ: 3%; 6º ANO JAN: 12%; 6º ANO FEV: 4%; 7º ANO MAR: 3%; 7º ANO ABR: 2%; 7º ANO MAI: 17%; 7º ANO JUN: 8%; 7º ANO JUL: 5%; 7º ANO AGO: 2%; 7º ANO SET: 9%; 7º ANO OUT: 0%; 7º ANO NOV: 1%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 95%
| km 507,850 ao km 508,551 - Pista Sul - São Joaquim de Bicas/MG - 0,701 km (correspondente ao km 507,900 ao km 508,400 - Pista Sul - São Joaquim de Bicas/MG - 0,500 km) | 507.85 | 508.551 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-04 | 2013-12-01 | 150 | 0% | PREVISTO | 6º ANO JUL: 22%; 6º ANO AGO: 5%; 6º ANO SET: 5%; 6º ANO OUT: 15%; 6º ANO NOV: 25%; 6º ANO DEZ: 28% | PREVISTO | 73% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 22%; 6º ANO AGO: 5%; 6º ANO SET: 7%; 6º ANO OUT: 16%; 6º ANO NOV: 29%; 6º ANO DEZ: 3%; 6º ANO JAN: 10%; 6º ANO FEV: 5%; 7º ANO MAR: 2%; 7º ANO ABR: 1%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 73%
| km 534,000 ao km 535,625 - Pista Sul - Itatiaiuçu/MG - 1,625 km (correspondente ao km 534,200 ao km 535,500 - Pista Sul - Itatiaiauçu/MG - 1,300 km) | 534 | 535.625 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-01-23 | 2013-11-30 | 311 | 20% | PREVISTO | 6º ANO MAR: 10%; 6º ANO ABR: 15%; 6º ANO MAI: 1%; 6º ANO JUN: 2%; 6º ANO JUL: 11%; 6º ANO AGO: 5%; 6º ANO SET: 8%; 6º ANO OUT: 13%; 6º ANO NOV: 15% | PREVISTO | 36% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 10% | 15% | 1% | 2% | 11% | 5% | 14% | 16% | 5% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [13 empty] | EXECUTADO | 36%
| km 561,085 ao km 561,645 - Pista Norte - Itaguara/MG - 0,560 km (correspondente ao km 561,100 ao km 562,000 - Pista Norte - Itaguara/MG - 0,900 km) | 561.085 | 561.645 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-22 | 2013-12-19 | 150 | 0% | PREVISTO | 6º ANO JUL: 4%; 6º ANO AGO: 6%; 6º ANO SET: 5%; 6º ANO OUT: 20%; 6º ANO NOV: 27%; 6º ANO DEZ: 38% | PREVISTO | 90% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 10%; 6º ANO SET: 6%; 6º ANO OUT: 2%; 6º ANO NOV: 1%; 6º ANO DEZ: 10%; 6º ANO JAN: 17%; 6º ANO FEV: 13%; 7º ANO MAR: 2%; 7º ANO ABR: 7%; 7º ANO MAI: 7%; 7º ANO JUN: 4%; 7º ANO JUL: 10%; 7º ANO AGO: 6%; 7º ANO SET: 5%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 90%
| km 561,775 ao km 562,765 - Pista Norte - Itaguara/MG - 0,990 km (correspondente ao km 562,400 ao km 562,700 - Pista Norte - Itaguara/MG - 0,300 km) | 561.775 | 562.765 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-09-01 | 2014-02-28 | 180 | 0% | PREVISTO | 6º ANO SET: 4%; 6º ANO OUT: 6%; 6º ANO NOV: 12%; 6º ANO DEZ: 20%; 6º ANO JAN: 28%; 6º ANO FEV: 30% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 23%; 6º ANO OUT: 15%; 6º ANO NOV: 8%; 6º ANO DEZ: 28%; 6º ANO JAN: 10%; 6º ANO FEV: 13%; 7º ANO MAR: 1%; 7º ANO ABR: 1%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 1%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 564,318 ao km 564,800 - Pista Norte - Itaguara/MG - 0,482 km (Correspondente ao km 564,500 ao km 564,700 - Pista Norte - Itaguara/MG - 0,200 km) | 564.318 | 564.8 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-09-01 | 2014-02-28 | 180 | 0% | PREVISTO | 6º ANO SET: 4%; 6º ANO OUT: 8%; 6º ANO NOV: 12%; 6º ANO DEZ: 20%; 6º ANO JAN: 25%; 6º ANO FEV: 31% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 18%; 6º ANO OUT: 21%; 6º ANO NOV: 22%; 6º ANO DEZ: 12%; 6º ANO JAN: 26%; 6º ANO FEV: 0%; 7º ANO MAR: 1%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 588,600 ao km 590,400 - Pista Norte - Carmópolis de Minas/MG - 1,800 km (Correspondente ao km 588,600 ao km 590,400 - Pista Norte - Carmópolis de Minas/MG - 1,800 km) | 588.6 | 590.4 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-10-01 | 2014-02-28 | 150 | 0% | PREVISTO | 6º ANO OUT: 12%; 6º ANO NOV: 17%; 6º ANO DEZ: 17%; 6º ANO JAN: 30%; 6º ANO FEV: 24% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO OUT: 6%; 6º ANO NOV: 1%; 6º ANO DEZ: 0%; 6º ANO JAN: 1%; 6º ANO FEV: 11%; 7º ANO MAR: 14%; 7º ANO ABR: 16%; 7º ANO MAI: 6%; 7º ANO JUN: 17%; 7º ANO JUL: 9%; 7º ANO AGO: 11%; 7º ANO SET: 6%; 7º ANO OUT: 1%; 7º ANO NOV: 1%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 588,762 ao km 589,857 - Pista Sul - Carmópolis de Minas/MG - 1,095 km (correspondente ao km 588,800 ao km 589,500 - Pista Sul - Carmópolis de Minas/MG - 0,700 km) | 588.762 | 589.857 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-09-01 | 2014-02-28 | 180 | 0% | PREVISTO | 6º ANO SET: 4%; 6º ANO OUT: 8%; 6º ANO NOV: 12%; 6º ANO DEZ: 20%; 6º ANO JAN: 25%; 6º ANO FEV: 31% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 0%; 6º ANO OUT: 6%; 6º ANO NOV: 1%; 6º ANO DEZ: 3%; 6º ANO JAN: 9%; 6º ANO FEV: 31%; 7º ANO MAR: 32%; 7º ANO ABR: 16%; 7º ANO MAI: 2%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 662,112 ao km 662,760 - Pista Norte - Perdões/MG - 0,648 km (correspondente ao km 662,200 ao km 662,670 - Pista Norte - Perdões/MG - 0,470 km) | 662.112 | 662.76 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-02-01 | 2014-05-31 | 119 | 0% | PREVISTO | 6º ANO FEV: 8%; 7º ANO MAR: 12%; 7º ANO ABR: 38%; 7º ANO MAI: 42% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO OUT: 18%; 6º ANO NOV: 2%; 6º ANO DEZ: 5%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 27%; 7º ANO JUL: 22%; 7º ANO AGO: 21%; 7º ANO SET: 4%; 7º ANO OUT: 0%; 7º ANO NOV: 1%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 666,900 ao km 667,700 - Pista Norte - Perdões/MG - 0,800 km (Correspondente ao km 666,900 ao km 667,700 - Pista Norte - Perdões/MG - 0,800 km | 666.9 | 667.7 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-08-05 | 2014-02-28 | 207 | 0% | PREVISTO | 6º ANO AGO: 14%; 6º ANO SET: 4%; 6º ANO OUT: 4%; 6º ANO NOV: 7%; 6º ANO DEZ: 17%; 6º ANO JAN: 24%; 6º ANO FEV: 30% | PREVISTO | 86% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 14%; 6º ANO SET: 13%; 6º ANO OUT: 27%; 6º ANO NOV: 5%; 6º ANO DEZ: 4%; 6º ANO JAN: 31%; 6º ANO FEV: 5%; 7º ANO MAR: 1%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 86%
| km 684,470 ao km 685,092 - Pista Sul - Perdões/MG - 0,622 km (correspondente ao km 684,500 ao km 684,960 - Pista Sul - Perdões/MG - 0,460 km) | 684.47 | 685.092 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-02-01 | 2014-05-31 | 119 | 0% | PREVISTO | 6º ANO FEV: 8%; 7º ANO MAR: 12%; 7º ANO ABR: 38%; 7º ANO MAI: 42% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO FEV: 11%; 7º ANO MAR: 1%; 7º ANO ABR: 4%; 7º ANO MAI: 43%; 7º ANO JUN: 21%; 7º ANO JUL: 15%; 7º ANO AGO: 4%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 1%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 723,400 ao km 723,904 - Pista Norte - Carmo da Cachoeira/MG - 0,504 km (correspondente ao km 723,350 ao km 723,750 - Pista Norte - Carmo da Cachoeira/MG - 0,400 km) | 723.4 | 723.904 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-06-26 | 2014-01-23 | 211 | 0% | PREVISTO | 6º ANO JUN: 14%; 6º ANO JUL: 20%; 6º ANO AGO: 5%; 6º ANO OUT: 8%; 6º ANO NOV: 15%; 6º ANO DEZ: 20%; 6º ANO JAN: 18% | PREVISTO | 61% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUN: 14%; 6º ANO JUL: 20%; 6º ANO AGO: 5%; 6º ANO SET: 27%; 6º ANO OUT: 8%; 6º ANO NOV: 23%; 6º ANO DEZ: 2%; 6º ANO JAN: 1%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 61%
| km 869+420 ao km 870+875 - Pista Sul - Pouso Alegre/MG - 1,455 km (Correspondente ao km 869,200 ao km 870,850 - Pista Sul - Pouso Alegre/MG - 1,650 km) | 869.42 | 870.875 | APROVADO | LICENCIADA | PUBLICADO (23/04/2014) | 2014-02-16 | 2014-08-15 | 180 | 0% | PREVISTO | 6º ANO FEV: 12%; 7º ANO MAR: 17%; 7º ANO ABR: 17%; 7º ANO MAI: 12%; 7º ANO JUN: 17%; 7º ANO JUL: 15%; 7º ANO AGO: 10% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO FEV: 7%; 7º ANO MAR: 9%; 7º ANO ABR: 12%; 7º ANO MAI: 15%; 7º ANO JUN: 12%; 7º ANO JUL: 27%; 7º ANO AGO: 15%; 7º ANO SET: 2%; 7º ANO OUT: 0%; 7º ANO NOV: 1%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 866,070 ao km 869,127 - Pista Norte - Pouso Alegre/MG - 3,057 km (correspondente ao km 866,400 ao km 869,200 - Pista Norte - Pouso Alegre/MG - 2,800 km) | 866.07 | 869.127 | APROVADO | LICENCIADA | PUBLICADO (23/04/2014) | 2013-01-25 | 2013-10-23 | 271 | 3% | PREVISTO | 6º ANO MAR: 2%; 6º ANO ABR: 5%; 6º ANO MAI: 11%; 6º ANO JUN: 16%; 6º ANO JUL: 27%; 6º ANO AGO: 9%; 6º ANO SET: 12%; 6º ANO OUT: 15% | PREVISTO | 27% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 2% | 5% | 11% | 16% | 27% | 9% | 8% | 15% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [13 empty] | EXECUTADO | 27%
| km 877,177 ao km 877,990 - Pista Norte - Estiva/MG - 0,813 km (correspondente ao km 877,400 ao km 877,850 - Pista Norte - Estiva/MG - 0,450 km) | 877.177 | 877.99 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-05 | 2013-12-30 | 178 | 0% | PREVISTO | 6º ANO JUL: 15%; 6º ANO AGO: 8%; 6º ANO SET: 13%; 6º ANO OUT: 18%; 6º ANO NOV: 20%; 6º ANO DEZ: 26% | PREVISTO | 77% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 15%; 6º ANO AGO: 8%; 6º ANO SET: 57%; 6º ANO OUT: 17%; 6º ANO NOV: 3%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 77%
| km 898+610 ao km 899+486 - Pista Sul - Cambui/MG - 0,876 km (Correspondente ao km 898,800 ao km 899,400 - Pista Sul - Cambui/MG - 0,600 km) | 898.61 | 899.486 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-03-16 | 2014-07-16 | 122 | 0% | PREVISTO | 7º ANO MAR: 14%; 7º ANO ABR: 22%; 7º ANO MAI: 28%; 7º ANO JUN: 25%; 7º ANO JUL: 11% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO FEV: 14%; 7º ANO MAR: 2%; 7º ANO ABR: 3%; 7º ANO MAI: 9%; 7º ANO JUN: 42%; 7º ANO JUL: 22%; 7º ANO AGO: 8%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 935,070 ao km 936,265 - Pista Norte - Extrema/MG - 1,195 km (Correspondente ao km 935,300 ao km 936,250 - Pista Norte - Extrema/MG - 0,950 km) | 935.07 | 936.265 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-10-01 | 2014-03-30 | 180 | 0% | PREVISTO | 6º ANO OUT: 12%; 6º ANO NOV: 17%; 6º ANO DEZ: 17%; 6º ANO JAN: 12%; 6º ANO FEV: 23%; 7º ANO MAR: 19% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO OUT: 13%; 6º ANO NOV: 10%; 6º ANO DEZ: 3%; 6º ANO JAN: 5%; 6º ANO FEV: 3%; 7º ANO MAR: 3%; 7º ANO ABR: 1%; 7º ANO MAI: 19%; 7º ANO JUN: 16%; 7º ANO JUL: 12%; 7º ANO AGO: 13%; 7º ANO SET: 2%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 6,080 ao km 6,500 - Pista Sul - Vargem/SP - 0,420 km (correspondente ao km 6,200 ao km 6,500 - Pista Sul - Vargem/SP - 0,300 km) | 6.08 | 6.5 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-05-21 | 2013-11-17 | 180 | 0% | PREVISTO | 6º ANO MAI: 16%; 6º ANO JUN: 52%; 6º ANO JUL: 14%; 6º ANO AGO: 5%; 6º ANO SET: 4%; 6º ANO OUT: 5%; 6º ANO NOV: 4% | PREVISTO | 13% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAI: 16%; 6º ANO JUN: 52%; 6º ANO JUL: 14%; 6º ANO AGO: 5%; 6º ANO SET: 12%; 6º ANO OUT: 1%; 6º ANO JAN: 0% | EXECUTADO | 13%
| km 28,191 ao km 28,729 - Pista Sul - Atibaia/SP - 0,538 km (correspondente ao km 28,300 ao km 28,500 - Pista Sul - Atibaia/SP - 0,200 km) | 28.191 | 28.729 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-15 | 2014-02-11 | 211 | 0% | PREVISTO | 6º ANO JUL: 27%; 6º ANO AGO: 5%; 6º ANO OUT: 8%; 6º ANO NOV: 8%; 6º ANO DEZ: 10%; 6º ANO JAN: 17%; 6º ANO FEV: 25% | PREVISTO | 68% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 27%; 6º ANO AGO: 5%; 6º ANO SET: 29%; 6º ANO OUT: 39%; 6º ANO JAN: 0% | EXECUTADO | 68%
| km 30,724 ao km 31,363 - Pista Sul - Atibaia/SP - 0,639 km (Correspondente ao km 30,800 ao km 31,100 - Pista Sul - Atibaia/SP - 0,300 km) | 30.724 | 31.363 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-10-01 | 2014-02-28 | 150 | 0% | PREVISTO | 6º ANO OUT: 12%; 6º ANO NOV: 17%; 6º ANO DEZ: 17%; 6º ANO JAN: 30%; 6º ANO FEV: 24% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 56%; 6º ANO OUT: 24%; 6º ANO NOV: 16%; 6º ANO DEZ: 4%; 6º ANO JAN: 0% | EXECUTADO | 100%
| km 44,482 ao km 45,223 - Pista Sul - Atibaia/SP - 0,741 km (correspondente ao km 44,500 ao km 45,200 - Pista Sul - Atibaia/SP - 0,700 km) | 44.482 | 45.223 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-09-01 | 2014-02-28 | 180 | 0% | PREVISTO | 6º ANO AGO: 5%; 6º ANO SET: 4%; 6º ANO OUT: 7%; 6º ANO NOV: 14%; 6º ANO DEZ: 20%; 6º ANO JAN: 25%; 6º ANO FEV: 25% | PREVISTO | 95% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 5%; 6º ANO SET: 28%; 6º ANO OUT: 52%; 6º ANO NOV: 11%; 6º ANO DEZ: 4%; 6º ANO JAN: 0% | EXECUTADO | 95%
| km 47,523 ao km 48,122 - Pista Sul - Atibaia/SP - 0,599 km (correspondente ao km 47,700 ao km 48,000 - Pista Sul - Atibaia/SP - 0,300 km) | 47.523 | 48.122 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-10-01 | 2014-07-31 | 303 | 0% | PREVISTO | 6º ANO OUT: 5%; 6º ANO NOV: 10%; 6º ANO DEZ: 2%; 6º ANO JAN: 2%; 6º ANO FEV: 2%; 7º ANO MAR: 2%; 7º ANO ABR: 10%; 7º ANO MAI: 20%; 7º ANO JUN: 22%; 7º ANO JUL: 25% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO OUT: 13%; 6º ANO NOV: 2%; 6º ANO DEZ: 25%; 6º ANO JAN: 32%; 6º ANO FEV: 13%; 7º ANO MAR: 15% | EXECUTADO | 100%
| km 55+663 ao km 56+275 - Pista Norte - Mairiporã/SP - 0,612 km (Correspondente ao km 55,750 ao km 56,250 - Pista Norte - Mairiporã/SP - 0,500 km | 55.663 | 56.275 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-08-01 | 2014-01-31 | 183 | 0% | PREVISTO | 6º ANO AGO: 5%; 6º ANO SET: 15%; 6º ANO OUT: 15%; 6º ANO NOV: 20%; 6º ANO DEZ: 25%; 6º ANO JAN: 20% | PREVISTO | 95% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 5%; 6º ANO SET: 25%; 6º ANO OUT: 29%; 6º ANO NOV: 17%; 6º ANO DEZ: 11%; 6º ANO JAN: 10%; 6º ANO FEV: 3% | EXECUTADO | 95%
| km 59,146 ao km 59,635 - Pista Sul - Mairiporã/SP - 0,489 km (correspondente ao km 59,200 ao km 59,700 - Pista Sul - Mairiporã/SP - 0,500 km) | 59.146 | 59.635 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-01-25 | 2013-09-30 | 248 | 5% | PREVISTO | 6º ANO MAR: 1e-14%; 6º ANO ABR: 1e-14%; 6º ANO MAI: 64%; 6º ANO JUN: 6%; 6º ANO JUL: 7%; 6º ANO AGO: 8%; 6º ANO SET: 10% | PREVISTO | 10% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAR: 1e-14%; 6º ANO ABR: 1e-14%; 6º ANO MAI: 64%; 6º ANO JUN: 6%; 6º ANO JUL: 7%; 6º ANO AGO: 8%; 6º ANO SET: 8%; 6º ANO OUT: 1%; 6º ANO NOV: 1%; 6º ANO DEZ: 0%; 6º ANO JAN: 0% | EXECUTADO | 10%
| km 62,014 ao km 62,504 - Pista Norte - Mairiporã/SP - 0,490 km (correspondente ao km 62,100 ao km 62,500 - Pista Norte - Mairiporã/SP - 0,400 km) | 62.014 | 62.504 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-05 | 2014-02-05 | 215 | 0% | PREVISTO | 6º ANO JUL: 43%; 6º ANO AGO: 5%; 6º ANO OUT: 6%; 6º ANO NOV: 8%; 6º ANO DEZ: 10%; 6º ANO JAN: 13%; 6º ANO FEV: 15% | PREVISTO | 52% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 43%; 6º ANO AGO: 5%; 6º ANO SET: 18%; 6º ANO OUT: 33%; 6º ANO NOV: 1%; 6º ANO JAN: 0% | EXECUTADO | 52%
| km 68+220 ao km 68+939 - Pista Sul = 0,719 km, (correspondente ao km 68,000 ao km 68,700 - Pista Sul - Mairiporã/SP - 0,710 km) | 68.22 | 68.939 | APROVADO | LICENCIADA | PUBLICADO | 2013-09-01 | 2014-02-28 | 180 | 0% | PREVISTO | 6º ANO SET: 4%; 6º ANO OUT: 8%; 6º ANO NOV: 12%; 6º ANO DEZ: 20%; 6º ANO JAN: 25%; 6º ANO FEV: 31% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 9%; 6º ANO OUT: 10%; 6º ANO NOV: 10%; 6º ANO DEZ: 6%; 6º ANO JAN: 4%; 6º ANO FEV: 34%; 7º ANO MAR: 20%; 7º ANO ABR: 7% | EXECUTADO | 100%
| Contorno de Betim - Rua Lateral do retorno do Bairro São João - 1,570 km | - | - | APROVADO | LICENCIADA | PUBLICADO | 2012-06-22 | 2013-09-30 | 465 | 9% | PREVISTO | 6º ANO MAR: 13.25%; 6º ANO ABR: 38.75%; 6º ANO MAI: 3%; 6º ANO JUN: 3%; 6º ANO JUL: 14%; 6º ANO AGO: 8%; 6º ANO SET: 11% | PREVISTO | 11% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAR: 13.25%; 6º ANO ABR: 38.75%; 6º ANO MAI: 3%; 6º ANO JUN: 3%; 6º ANO JUL: 14%; 6º ANO AGO: 8%; 6º ANO SET: 10%; 6º ANO OUT: 1%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 11%
5.1.4. Melhoria de Acessos Existentes | km 477+370 - Pista Norte - Contagem /MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-06-06 | 2013-09-11 | 97 | 0% | PREVISTO | 6º ANO JUN: 40%; 6º ANO JUL: 34%; 6º ANO AGO: 13%; 6º ANO SET: 13% | PREVISTO | 13% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUN: 40%; 6º ANO JUL: 34%; 6º ANO AGO: 13%; 6º ANO SET: 13%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 13%
| km 477+370 - Pista Sul - Contagem/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-06-06 | 2013-09-11 | 97 | 0% | PREVISTO | 6º ANO JUN: 49%; 6º ANO JUL: 31%; 6º ANO AGO: 10%; 6º ANO SET: 10% | PREVISTO | 10% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUN: 49%; 6º ANO JUL: 31%; 6º ANO AGO: 10%; 6º ANO SET: 10%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 10%
| km 477+540 - Pista Norte - Contagem /MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-06-06 | 2013-09-11 | 97 | 0% | PREVISTO | 6º ANO JUN: 48%; 6º ANO JUL: 35%; 6º ANO AGO: 7%; 6º ANO SET: 10% | PREVISTO | 10% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUN: 48%; 6º ANO JUL: 35%; 6º ANO AGO: 7%; 6º ANO SET: 10%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 10%
| km 477+690 - Pista Norte - Contagem/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-06-06 | 2013-09-11 | 97 | 0% | PREVISTO | 6º ANO JUN: 40%; 6º ANO JUL: 44%; 6º ANO AGO: 6%; 6º ANO SET: 10% | PREVISTO | 10% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUN: 40%; 6º ANO JUL: 44%; 6º ANO AGO: 6%; 6º ANO SET: 10%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 10%
| km 488+460 - Pista Sul - Betim/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-16 | 2013-10-15 | 91 | 0% | PREVISTO | 6º ANO JUL: 32%; 6º ANO AGO: 36%; 6º ANO SET: 14%; 6º ANO OUT: 18% | PREVISTO | 32% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 32%; 6º ANO AGO: 36%; 6º ANO SET: 29%; 6º ANO OUT: 3%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 32%
| km 497+000 - Pista Norte - Betim/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-12 | 2013-10-11 | 91 | 0% | PREVISTO | 6º ANO JUL: 15%; 6º ANO AGO: 15%; 6º ANO SET: 35%; 6º ANO OUT: 35% | PREVISTO | 70% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 15%; 6º ANO AGO: 15%; 6º ANO SET: 4%; 6º ANO OUT: 0%; 6º ANO NOV: 0%; 6º ANO DEZ: 3%; 6º ANO JAN: 20%; 6º ANO FEV: 43%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 70%
| km 497+300 - Pista Sul - Betim/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-12 | 2013-10-11 | 91 | 0% | PREVISTO | 6º ANO JUL: 36%; 6º ANO AGO: 33%; 6º ANO SET: 12%; 6º ANO OUT: 19% | PREVISTO | 31% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 36%; 6º ANO AGO: 33%; 6º ANO SET: 15%; 6º ANO OUT: 13%; 6º ANO NOV: 3%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 31%
| km 501+600 - Pista Sul - Betim/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-11 | 2013-10-10 | 91 | 0% | PREVISTO | 6º ANO JUL: 30%; 6º ANO AGO: 42%; 6º ANO SET: 10%; 6º ANO OUT: 18% | PREVISTO | 28% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 30%; 6º ANO AGO: 42%; 6º ANO SET: 27%; 6º ANO OUT: 0%; 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 1%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 28%
| km 503+500 - Pista Sul - Betim/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-16 | 2013-10-15 | 91 | 0% | PREVISTO | 6º ANO JUL: 30%; 6º ANO AGO: 39%; 6º ANO SET: 12%; 6º ANO OUT: 19% | PREVISTO | 31% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 30%; 6º ANO AGO: 39%; 6º ANO SET: 28%; 6º ANO OUT: 3%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 31%
| km 36+800 - Pista Norte - Atibaia/SP | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-06-14 | 2013-09-12 | 90 | 0% | PREVISTO | 6º ANO JUN: 33%; 6º ANO JUL: 43%; 6º ANO AGO: 10%; 6º ANO SET: 14% | PREVISTO | 14% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUN: 33%; 6º ANO JUL: 43%; 6º ANO AGO: 10%; 6º ANO SET: 14%; 6º ANO OUT: 0%; 6º ANO JAN: 0% | EXECUTADO | 14%
| km 60+700 - Pista Norte - Mairiporã/SP | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-08-01 | 2013-10-30 | 90 | 0% | PREVISTO | 6º ANO AGO: 10%; 6º ANO SET: 20%; 6º ANO OUT: 70% | PREVISTO | 90% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 10%; 6º ANO SET: 90%; 6º ANO OUT: 0%; 6º ANO JAN: 0% | EXECUTADO | 90%
| km 63+800 - Pista Sul - Mairiporã/SP | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-17 | 2013-10-15 | 90 | 0% | PREVISTO | 6º ANO JUL: 66%; 6º ANO AGO: 10%; 6º ANO SET: 12%; 6º ANO OUT: 12% | PREVISTO | 24% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 66%; 6º ANO AGO: 10%; 6º ANO SET: 24%; 6º ANO OUT: 0%; 6º ANO JAN: 0% | EXECUTADO | 24%
| km 70+200 - Pista Norte - Mairiporã/SP | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-08-02 | 2013-10-31 | 90 | 0% | PREVISTO | 6º ANO AGO: 10%; 6º ANO SET: 20%; 6º ANO OUT: 70% | PREVISTO | 90% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 10%; 6º ANO SET: 90%; 6º ANO OUT: 0%; 6º ANO JAN: 0% | EXECUTADO | 90%
| km 71+000 - Pista Norte - Mairiporã/SP | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-10 | 2013-10-20 | 102 | 0% | PREVISTO | 6º ANO JUL: 71%; 6º ANO AGO: 9%; 6º ANO SET: 10%; 6º ANO OUT: 10% | PREVISTO | 20% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 71%; 6º ANO AGO: 9%; 6º ANO SET: 20%; 6º ANO OUT: 0%; 6º ANO JAN: 0% | EXECUTADO | 20%
| km 69+900 - Pista Sul - Mairiporã/SP | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-02-28 | 119 | 0% | PREVISTO | 6º ANO NOV: 5%; 6º ANO DEZ: 20%; 6º ANO JAN: 35%; 6º ANO FEV: 40% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO OUT: 0%; 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 95%; 7º ANO MAR: 5% | EXECUTADO | 100%
| km 59+250 - Pista Norte - Mairiporã/SP | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-02-28 | 119 | 0% | PREVISTO | 6º ANO NOV: 5%; 6º ANO DEZ: 20%; 6º ANO JAN: 35%; 6º ANO FEV: 40% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO OUT: 0%; 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 71%; 6º ANO FEV: 24%; 7º ANO MAR: 5% | EXECUTADO | 100%
| km 891+800 - Pista Norte - Cambuí/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-10-15 | 2014-01-15 | 92 | 0% | PREVISTO | 6º ANO AGO: 45%; 6º ANO SET: 0%; 6º ANO OUT: 5%; 6º ANO NOV: 9%; 6º ANO DEZ: 15%; 6º ANO JAN: 26% | PREVISTO | 55% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 45%; 6º ANO SET: 55%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 55%
| km 750+520 - Pista Sul - Três Corações/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-02-28 | 119 | 0% | PREVISTO | 6º ANO NOV: 5%; 6º ANO DEZ: 20%; 6º ANO JAN: 35%; 6º ANO FEV: 40% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 30%; 6º ANO JAN: 58%; 6º ANO FEV: 12%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 9+300 - Pista Norte - Vargem/SP | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-02-28 | 119 | 0% | PREVISTO | 6º ANO NOV: 5%; 6º ANO DEZ: 20%; 6º ANO JAN: 35%; 6º ANO FEV: 40% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 11%; 6º ANO JAN: 60%; 6º ANO FEV: 29% | EXECUTADO | 100%
| km 876+100 - Pista Norte - Estiva/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-02-28 | 119 | 0% | PREVISTO | 6º ANO NOV: 5%; 6º ANO DEZ: 20%; 6º ANO JAN: 35%; 6º ANO FEV: 40% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 61%; 6º ANO JAN: 39%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
5.1.5 Melhoria de Interseções Existentes | km 38+350 - Passagem Inferior | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-03-31 | 150 | 0% | PREVISTO | 6º ANO NOV: 15%; 6º ANO DEZ: 27%; 6º ANO JAN: 18%; 6º ANO FEV: 20%; 7º ANO MAR: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO OUT: 0%; 6º ANO NOV: 0%; 6º ANO DEZ: 15%; 6º ANO JAN: 65%; 6º ANO FEV: 20%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0% | EXECUTADO | 100%
| km 495,670 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-03-31 | 150 | 0% | PREVISTO | 6º ANO NOV: 15%; 6º ANO DEZ: 27%; 6º ANO JAN: 18%; 6º ANO FEV: 20%; 7º ANO MAR: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 63%; 7º ANO MAI: 27%; 7º ANO JUN: 0%; 7º ANO JUL: 5%; 7º ANO AGO: 3%; 7º ANO SET: 0%; 7º ANO OUT: 2%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 536,290 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-03-31 | 150 | 0% | PREVISTO | 6º ANO NOV: 15%; 6º ANO DEZ: 27%; 6º ANO JAN: 18%; 6º ANO FEV: 20%; 7º ANO MAR: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 52%; 7º ANO JUL: 0%; 7º ANO AGO: 43%; 7º ANO SET: 5%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 616,950 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-03-31 | 150 | 0% | PREVISTO | 6º ANO NOV: 15%; 6º ANO DEZ: 27%; 6º ANO JAN: 18%; 6º ANO FEV: 20%; 7º ANO MAR: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 67%; 7º ANO MAI: 23%; 7º ANO JUN: 0%; 7º ANO JUL: 5%; 7º ANO AGO: 4%; 7º ANO SET: 0%; 7º ANO OUT: 1%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 619,970 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-03-31 | 150 | 0% | PREVISTO | 6º ANO NOV: 15%; 6º ANO DEZ: 27%; 6º ANO JAN: 18%; 6º ANO FEV: 20%; 7º ANO MAR: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 58%; 7º ANO MAI: 32%; 7º ANO JUN: 0%; 7º ANO JUL: 5%; 7º ANO AGO: 4%; 7º ANO SET: 0%; 7º ANO OUT: 1%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 723,040 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-03-31 | 150 | 0% | PREVISTO | 6º ANO NOV: 15%; 6º ANO DEZ: 27%; 6º ANO JAN: 18%; 6º ANO FEV: 20%; 7º ANO MAR: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 35%; 7º ANO MAI: 55%; 7º ANO JUN: 0%; 7º ANO JUL: 5%; 7º ANO AGO: 5%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 850,270 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-03-31 | 150 | 0% | PREVISTO | 6º ANO NOV: 15%; 6º ANO DEZ: 27%; 6º ANO JAN: 18%; 6º ANO FEV: 20%; 7º ANO MAR: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 63%; 7º ANO ABR: 36%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 1%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 869,400 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-03-31 | 150 | 0% | PREVISTO | 6º ANO NOV: 15%; 6º ANO DEZ: 27%; 6º ANO JAN: 18%; 6º ANO FEV: 20%; 7º ANO MAR: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 90%; 7º ANO JUN: 5%; 7º ANO JUL: 0%; 7º ANO AGO: 5%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 887,200 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-03-31 | 150 | 0% | PREVISTO | 6º ANO NOV: 15%; 6º ANO DEZ: 27%; 6º ANO JAN: 18%; 6º ANO FEV: 20%; 7º ANO MAR: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 74%; 7º ANO MAI: 16%; 7º ANO JUN: 0%; 7º ANO JUL: 5%; 7º ANO AGO: 5%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 933,000 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-03-31 | 150 | 0% | PREVISTO | 6º ANO NOV: 15%; 6º ANO DEZ: 27%; 6º ANO JAN: 18%; 6º ANO FEV: 20%; 7º ANO MAR: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 39%; 7º ANO JUN: 13%; 7º ANO JUL: 43%; 7º ANO AGO: 5%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 941,510 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-03-31 | 150 | 0% | PREVISTO | 6º ANO NOV: 15%; 6º ANO DEZ: 27%; 6º ANO JAN: 18%; 6º ANO FEV: 20%; 7º ANO MAR: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 10%; 7º ANO JUL: 85%; 7º ANO AGO: 5%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 50,450 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-03-31 | 150 | 0% | PREVISTO | 6º ANO NOV: 15%; 6º ANO DEZ: 27%; 6º ANO JAN: 18%; 6º ANO FEV: 20%; 7º ANO MAR: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO OUT: 0%; 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 24%; 7º ANO MAI: 48%; 7º ANO JUN: 22%; 7º ANO JUL: 6% | EXECUTADO | 100%
| km 480,565 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-06-01 | 2014-10-31 | 152 | 0% | PREVISTO | 7º ANO JUN: 12%; 7º ANO JUL: 17%; 7º ANO AGO: 17%; 7º ANO SET: 30%; 7º ANO OUT: 24% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 7º ANO ABR: 12%; 7º ANO MAI: 33%; 7º ANO JUN: 35%; 7º ANO JUL: 3%; 7º ANO AGO: 9%; 7º ANO SET: 8%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 529,885 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-06-01 | 2014-10-31 | 152 | 0% | PREVISTO | 7º ANO JUN: 12%; 7º ANO JUL: 17%; 7º ANO AGO: 17%; 7º ANO SET: 30%; 7º ANO OUT: 24% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 7º ANO ABR: 0%; 7º ANO MAI: 34%; 7º ANO JUN: 36%; 7º ANO JUL: 3%; 7º ANO AGO: 17%; 7º ANO SET: 10%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 533,120 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-06-01 | 2014-10-31 | 152 | 0% | PREVISTO | 7º ANO JUN: 12%; 7º ANO JUL: 17%; 7º ANO AGO: 17%; 7º ANO SET: 30%; 7º ANO OUT: 24% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 7º ANO ABR: 30%; 7º ANO MAI: 60%; 7º ANO JUN: 0%; 7º ANO JUL: 5%; 7º ANO AGO: 3%; 7º ANO SET: 2%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 650,130 | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-06-01 | 2014-10-31 | 152 | 0% | PREVISTO | 7º ANO JUN: 12%; 7º ANO JUL: 17%; 7º ANO AGO: 17%; 7º ANO SET: 30%; 7º ANO OUT: 24% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 7º ANO ABR: 28%; 7º ANO MAI: 62%; 7º ANO JUN: 0%; 7º ANO JUL: 5%; 7º ANO AGO: 4%; 7º ANO SET: 1%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
5.1.9 Implantação de Trevos em Desnível, com Alças, em Pista Dupla - Parcial - 3 unidades | km 586+025 - Carmópolis de Minas/MG (Localização a ser transferida para o item 5.1.10 - Trevo Completo) | - | - | APROVADO | LICENCIADA | PUBLICADO | 2012-08-09 | 2013-09-30 | 417 | 68% | PREVISTO | 6º ANO MAR: 4%; 6º ANO ABR: 3%; 6º ANO MAI: 6%; 6º ANO JUN: 1%; 6º ANO JUL: 8%; 6º ANO AGO: 2%; 6º ANO SET: 8% | PREVISTO | 8% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 4% | 3% | 6% | 1% | 8% | 2% | 5% | 2% | 1% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [13 empty] | EXECUTADO | 8%
| km 506+600 - São Joaquim de Bicas/MG | - | - | APROVADO | LICENCIADA | PUBLICADO (13/11/2014) | 2014-08-01 | 2015-06-28 | 331 | 0% | PREVISTO | 7º ANO AGO: 2%; 7º ANO SET: 5%; 7º ANO OUT: 6%; 7º ANO NOV: 4%; 7º ANO DEZ: 7%; 7º ANO JAN: 7%; 7º ANO FEV: 8%; 7º ANO MAR: 13%; 7º ANO ABR: 14%; 7º ANO MAI: 16%; 7º ANO JUN: 18% | PREVISTO | 39% | ADIANTADA | 52%
[11 empty] | EXECUTADO | 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 5%; 7º ANO SET: 10%; 7º ANO OUT: 6%; 7º ANO NOV: 16%; 7º ANO DEZ: 8%; 7º ANO JAN: 5%; 7º ANO FEV: 2% | EXECUTADO | 52%
5.1.10. Implantação de Trevos em Desnível, com Alças, em Pista Dupla - Completo - 5 unidades | km 494+040 - Betim/MG |  |  | APROVADO | LICENCIADA | PUBLICADO (14/11/2014) | 2014-08-01 | 2015-06-28 |  | 0% | PREVISTO | 7º ANO AGO: 2%; 7º ANO SET: 5%; 7º ANO OUT: 6%; 7º ANO NOV: 4%; 7º ANO DEZ: 7%; 7º ANO JAN: 7%; 7º ANO FEV: 8%; 7º ANO MAR: 13%; 7º ANO ABR: 14%; 7º ANO MAI: 16%; 7º ANO JUN: 18% | PREVISTO | 39% | ADIANTADA | 62%
[11 empty] | EXECUTADO | 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 6%; 7º ANO SET: 5%; 7º ANO OUT: 7%; 7º ANO NOV: 17%; 7º ANO DEZ: 10%; 7º ANO JAN: 12%; 7º ANO FEV: 5% | EXECUTADO | 62%
5.1.14 Execução de Passarelas sobre Pista Dupla - 50 unidades | km 477+765 - Contagem/MG (Antigo km 477+690) | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-06-10 | 2014-02-28 | 263 | 0% | PREVISTO | 6º ANO JUN: 15%; 6º ANO JUL: 6%; 6º ANO AGO: 7%; 6º ANO SET: 8%; 6º ANO OUT: 7%; 6º ANO NOV: 7%; 6º ANO DEZ: 15%; 6º ANO JAN: 17%; 6º ANO FEV: 18% | PREVISTO | 72% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUN: 15%; 6º ANO JUL: 6%; 6º ANO AGO: 7%; 6º ANO SET: 39%; 6º ANO OUT: 30%; 6º ANO NOV: 2%; 6º ANO DEZ: 1%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 72%
| km 485+100 - Betim/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-05-22 | 2014-03-28 | 310 | 0% | PREVISTO | 6º ANO MAI: 10%; 6º ANO JUN: 20%; 6º ANO JUL: 34%; 6º ANO AGO: 12%; 6º ANO SET: 0%; 6º ANO OUT: 4%; 6º ANO NOV: 4%; 6º ANO DEZ: 3%; 6º ANO JAN: 4%; 6º ANO FEV: 3%; 7º ANO MAR: 6% | PREVISTO | 24% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAI: 10%; 6º ANO JUN: 20%; 6º ANO JUL: 34%; 6º ANO AGO: 12%; 6º ANO SET: 16%; 6º ANO OUT: 5%; 6º ANO NOV: 2%; 6º ANO DEZ: 1%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 24%
| km 493+300 - Betim/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-05-28 | 2014-03-28 | 304 | 0% | PREVISTO | 6º ANO MAI: 13%; 6º ANO JUN: 8%; 6º ANO JUL: 31%; 6º ANO AGO: 4%; 6º ANO SET: 0%; 6º ANO OUT: 5%; 6º ANO NOV: 4%; 6º ANO DEZ: 6%; 6º ANO JAN: 7%; 6º ANO FEV: 10%; 7º ANO MAR: 12% | PREVISTO | 44% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAI: 13%; 6º ANO JUN: 8%; 6º ANO JUL: 31%; 6º ANO AGO: 4%; 6º ANO SET: 31%; 6º ANO OUT: 8%; 6º ANO NOV: 3%; 6º ANO DEZ: 2%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 44%
| km 494+750 - Betim/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-08-15 | 2014-02-28 | 197 | 0% | PREVISTO | 6º ANO AGO: 10%; 6º ANO SET: 7%; 6º ANO OUT: 9%; 6º ANO NOV: 17%; 6º ANO DEZ: 16%; 6º ANO JAN: 17%; 6º ANO FEV: 24% | PREVISTO | 90% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 10%; 6º ANO SET: 26%; 6º ANO OUT: 28%; 6º ANO NOV: 22%; 6º ANO DEZ: 10%; 6º ANO JAN: 1%; 6º ANO FEV: 3%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 90%
| km 497+045 - Betim/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2012-10-01 | 2013-11-30 | 425 | 28% | PREVISTO | 6º ANO MAR: 2%; 6º ANO ABR: 1e-23%; 6º ANO MAI: 1e-23%; 6º ANO JUN: 1%; 6º ANO JUL: 20%; 6º ANO AGO: 24%; 6º ANO SET: 7%; 6º ANO OUT: 7%; 6º ANO NOV: 11% | PREVISTO | 25% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 2% | 1e-23% | 1e-23% | 1% | 20% | 24% | 17% | 5% | 3% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [13 empty] | EXECUTADO | 25%
| km 508+300 - São Joaquim de Bicas/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-03 | 2014-02-28 | 240 | 0% | PREVISTO | 6º ANO JUL: 30%; 6º ANO AGO: 20%; 6º ANO SET: 2%; 6º ANO OUT: 3%; 6º ANO NOV: 5%; 6º ANO DEZ: 8%; 6º ANO JAN: 14%; 6º ANO FEV: 18% | PREVISTO | 50% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 30%; 6º ANO AGO: 20%; 6º ANO SET: 33%; 6º ANO OUT: 11%; 6º ANO NOV: 5%; 6º ANO DEZ: 1%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 50%
| km 510+800 - São Joaquim de Bicas/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-10-01 | 2014-07-31 | 303 | 0% | PREVISTO | 6º ANO AGO: 10%; 6º ANO SET: 0%; 6º ANO OUT: 3%; 6º ANO NOV: 3%; 6º ANO DEZ: 5%; 6º ANO JAN: 6%; 6º ANO FEV: 11%; 7º ANO MAR: 6%; 7º ANO ABR: 9%; 7º ANO MAI: 14%; 7º ANO JUN: 16%; 7º ANO JUL: 17% | PREVISTO | 90% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 10%; 6º ANO SET: 11%; 6º ANO OUT: 4%; 6º ANO NOV: 53%; 6º ANO DEZ: 4%; 6º ANO JAN: 11%; 6º ANO FEV: 7%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 90%
| km 534+900 - Itatiaiuçu/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-05-27 | 2014-02-28 | 277 | 0% | PREVISTO | 6º ANO MAI: 10%; 6º ANO JUN: 1e-23%; 6º ANO JUL: 15%; 6º ANO AGO: 15%; 6º ANO SET: 3%; 6º ANO OUT: 3%; 6º ANO NOV: 5%; 6º ANO DEZ: 12%; 6º ANO JAN: 17%; 6º ANO FEV: 20% | PREVISTO | 60% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAI: 10%; 6º ANO JUN: 1e-23%; 6º ANO JUL: 15%; 6º ANO AGO: 15%; 6º ANO SET: 4%; 6º ANO OUT: 23%; 6º ANO NOV: 22%; 6º ANO DEZ: 10%; 6º ANO JAN: 0%; 6º ANO FEV: 1%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 60%
| km 564+700 - Itaguara/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-10-01 | 2014-07-31 | 303 | 0% | PREVISTO | 6º ANO AGO: 12%; 6º ANO SET: 0%; 6º ANO OUT: 2%; 6º ANO NOV: 3%; 6º ANO DEZ: 5%; 6º ANO JAN: 6%; 6º ANO FEV: 9%; 7º ANO MAR: 8%; 7º ANO ABR: 10%; 7º ANO MAI: 10%; 7º ANO JUN: 17%; 7º ANO JUL: 18% | PREVISTO | 88% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 12%; 6º ANO SET: 3%; 6º ANO OUT: 11%; 6º ANO NOV: 50%; 6º ANO DEZ: 7%; 6º ANO JAN: 15%; 6º ANO FEV: 2%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 88%
| km 582+600 - Carmópolis de Minas/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-10-01 | 2014-07-31 | 303 | 0% | PREVISTO | 6º ANO OUT: 2%; 6º ANO NOV: 3%; 6º ANO DEZ: 5%; 6º ANO JAN: 6%; 6º ANO FEV: 11%; 7º ANO MAR: 11%; 7º ANO ABR: 12%; 7º ANO MAI: 15%; 7º ANO JUN: 17%; 7º ANO JUL: 18% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 0%; 6º ANO OUT: 12%; 6º ANO NOV: 38%; 6º ANO DEZ: 6%; 6º ANO JAN: 3%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 10%; 7º ANO MAI: 4%; 7º ANO JUN: 7%; 7º ANO JUL: 1%; 7º ANO AGO: 6%; 7º ANO SET: 1%; 7º ANO OUT: 5%; 7º ANO NOV: 7%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 816+400 - Careaçu/MG (Antigo km 617+300) | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-12-01 | 2014-09-30 | 303 | 0% | PREVISTO | 6º ANO DEZ: 2%; 6º ANO JAN: 3%; 6º ANO FEV: 5%; 7º ANO MAR: 6%; 7º ANO ABR: 11%; 7º ANO MAI: 11%; 7º ANO JUN: 12%; 7º ANO JUL: 15%; 7º ANO AGO: 17%; 7º ANO SET: 18% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 44%; 6º ANO DEZ: 24%; 6º ANO JAN: 16%; 6º ANO FEV: 8%; 7º ANO MAR: 5%; 7º ANO ABR: 1%; 7º ANO MAI: 2%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 675+540 - Perdões/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-02-08 | 2013-12-31 | 326 | 12% | PREVISTO | 6º ANO MAR: 18%; 6º ANO ABR: 1e-23%; 6º ANO MAI: 50%; 6º ANO JUN: 1%; 6º ANO JUL: 6%; 6º ANO AGO: 2%; 6º ANO SET: 3%; 6º ANO OUT: 2%; 6º ANO NOV: 3%; 6º ANO DEZ: 3% | PREVISTO | 11% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 18% | 1e-23% | 50% | 1% | 6% | 2% | 7% | 4% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [13 empty] | EXECUTADO | 11%
| km 754+400 - Três Corações/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2012-10-15 | 2013-09-30 | 350 | 30% | PREVISTO | 6º ANO MAR: 1e-23%; 6º ANO ABR: 1e-23%; 6º ANO MAI: 1e-23%; 6º ANO JUN: 29%; 6º ANO JUL: 10%; 6º ANO AGO: 18%; 6º ANO SET: 13% | PREVISTO | 13% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 1e-23% | 1e-23% | 1e-23% | 29% | 10% | 18% | 7% | 6% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [13 empty] | EXECUTADO | 13%
| km 755+000 - Três Corações/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-22 | 2014-02-28 | 221 | 0% | PREVISTO | 6º ANO JUL: 6%; 6º ANO AGO: 30%; 6º ANO SET: 6%; 6º ANO OUT: 9%; 6º ANO NOV: 6%; 6º ANO DEZ: 9%; 6º ANO JAN: 15%; 6º ANO FEV: 19% | PREVISTO | 64% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 6%; 6º ANO AGO: 30%; 6º ANO SET: 18%; 6º ANO OUT: 39%; 6º ANO NOV: 7%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 64%
| km 850+000 - Pouso Alegre/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2012-12-17 | 2013-11-17 | 335 | 30% | PREVISTO | 6º ANO MAR: 1e-23%; 6º ANO ABR: 1e-23%; 6º ANO MAI: 1e-23%; 6º ANO JUN: 1e-23%; 6º ANO JUL: 33%; 6º ANO AGO: 7%; 6º ANO SET: 8%; 6º ANO OUT: 10%; 6º ANO NOV: 12% | PREVISTO | 30% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 1e-23% | 1e-23% | 1e-23% | 1e-23% | 33% | 7% | 10% | 13% | 7% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [13 empty] | EXECUTADO | 30%
| km 877+400 - Estiva/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-02-25 | 2013-12-22 | 300 | 6% | PREVISTO | 6º ANO MAR: 6%; 6º ANO ABR: 6%; 6º ANO MAI: 6%; 6º ANO JUN: 6%; 6º ANO JUL: 22%; 6º ANO AGO: 20%; 6º ANO SET: 2%; 6º ANO OUT: 7%; 6º ANO NOV: 9%; 6º ANO DEZ: 10% | PREVISTO | 28% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6% | 6% | 6% | 6% | 22% | 20% | 10% | 3% | 13% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [13 empty] | EXECUTADO | 28%
| km 928+450 - Itapeva/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-02-15 | 2013-11-30 | 288 | 15% | PREVISTO | 6º ANO MAR: 27%; 6º ANO ABR: 4%; 6º ANO MAI: 18%; 6º ANO JUN: 13%; 6º ANO JUL: 16%; 6º ANO AGO: 2%; 6º ANO SET: 1%; 6º ANO OUT: 2%; 6º ANO NOV: 2% | PREVISTO | 5% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 27% | 4% | 18% | 13% | 16% | 2% | 2% | 3% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [13 empty] | EXECUTADO | 5%
| km 939+000 - Extrema/MG | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-10-01 | 2014-07-31 | 303 | 0% | PREVISTO | 6º ANO OUT: 2%; 6º ANO NOV: 3%; 6º ANO DEZ: 5%; 6º ANO JAN: 6%; 6º ANO FEV: 11%; 7º ANO MAR: 11%; 7º ANO ABR: 12%; 7º ANO MAI: 15%; 7º ANO JUN: 17%; 7º ANO JUL: 18% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 7%; 6º ANO OUT: 4%; 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 10%; 6º ANO FEV: 5%; 7º ANO MAR: 30%; 7º ANO ABR: 20%; 7º ANO MAI: 9%; 7º ANO JUN: 11%; 7º ANO JUL: 4%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 29+500 - Atibaia/SP | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2012-05-10 | 2013-11-30 | 569 | 0.5% | PREVISTO | 6º ANO MAR: 11%; 6º ANO ABR: 9%; 6º ANO MAI: 1e-23%; 6º ANO JUN: 4.5%; 6º ANO JUL: 2%; 6º ANO AGO: 6%; 6º ANO SET: 21%; 6º ANO OUT: 26%; 6º ANO NOV: 20% | PREVISTO | 67% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAR: 11%; 6º ANO ABR: 9%; 6º ANO MAI: 1e-23%; 6º ANO JUN: 4.5%; 6º ANO JUL: 2%; 6º ANO AGO: 6%; 6º ANO SET: 22%; 6º ANO OUT: 29%; 6º ANO NOV: 10%; 6º ANO DEZ: 6%; 6º ANO JAN: 0% | EXECUTADO | 67%
| km 30+500 - Atibaia/SP | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-04 | 2014-03-28 | 267 | 0% | PREVISTO | 6º ANO JUL: 11%; 6º ANO AGO: 6%; 6º ANO SET: 0%; 6º ANO OUT: 4%; 6º ANO NOV: 12%; 6º ANO DEZ: 12%; 6º ANO JAN: 14%; 6º ANO FEV: 16%; 7º ANO MAR: 25% | PREVISTO | 83% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 11%; 6º ANO AGO: 6%; 6º ANO SET: 26%; 6º ANO OUT: 12%; 6º ANO NOV: 8%; 6º ANO DEZ: 28%; 6º ANO JAN: 7%; 6º ANO FEV: 2%; 7º ANO MAR: 0% | EXECUTADO | 83%
| km 40+300 - Atibaia/SP | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2012-08-06 | 2013-10-31 | 451 | 32% | PREVISTO | 6º ANO MAR: 30%; 6º ANO ABR: 0.5%; 6º ANO MAI: 10%; 6º ANO JUN: 8.5%; 6º ANO JUL: 3%; 6º ANO AGO: 5%; 6º ANO SET: 5%; 6º ANO OUT: 6% | PREVISTO | 11% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAR: 30%; 6º ANO ABR: 0.5%; 6º ANO MAI: 10%; 6º ANO JUN: 8.5%; 6º ANO JUL: 3%; 6º ANO AGO: 5%; 6º ANO SET: 5%; 6º ANO OUT: 6%; 6º ANO NOV: 0%; 6º ANO JAN: 0% | EXECUTADO | 11%
| km 47+750 - Atibaia/SP | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-05-14 | 2014-02-28 | 290 | 0% | PREVISTO | 6º ANO MAI: 5%; 6º ANO JUN: 12%; 6º ANO JUL: 9%; 6º ANO AGO: 2%; 6º ANO SET: 3%; 6º ANO OUT: 2%; 6º ANO NOV: 12%; 6º ANO DEZ: 14%; 6º ANO JAN: 16%; 6º ANO FEV: 25% | PREVISTO | 72% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAI: 5%; 6º ANO JUN: 12%; 6º ANO JUL: 9%; 6º ANO AGO: 2%; 6º ANO SET: 16%; 6º ANO OUT: 7%; 6º ANO NOV: 8%; 6º ANO DEZ: 25%; 6º ANO JAN: 4%; 6º ANO FEV: 3%; 7º ANO MAR: 4%; 7º ANO ABR: 1%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 4% | EXECUTADO | 72%
| km 52+800 - Mairiporã/SP | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-07-02 | 2014-02-28 | 241 | 0% | PREVISTO | 6º ANO JUL: 5%; 6º ANO AGO: 6%; 6º ANO SET: 10%; 6º ANO OUT: 12%; 6º ANO NOV: 12%; 6º ANO DEZ: 14%; 6º ANO JAN: 16%; 6º ANO FEV: 25% | PREVISTO | 89% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 5%; 6º ANO AGO: 6%; 6º ANO SET: 37%; 6º ANO OUT: 10%; 6º ANO NOV: 11%; 6º ANO DEZ: 4%; 6º ANO JAN: 5%; 6º ANO FEV: 9%; 7º ANO MAR: 3%; 7º ANO ABR: 2%; 7º ANO MAI: 8%; 7º ANO JUN: 0% | EXECUTADO | 89%
5.1.19. Implantação de Retorno Operacional | km 8+300 - Retorno Operacional | - | - | APROVADO | LICENCIADA | PUBLICADO | 2012-09-18 | 2013-12-31 | 469 | 5% | PREVISTO | 6º ANO MAR: 1e-06%; 6º ANO ABR: 0.5%; 6º ANO MAI: 2.5%; 6º ANO JUN: 1%; 6º ANO JUL: 6%; 6º ANO AGO: 10%; 6º ANO SET: 16%; 6º ANO OUT: 16%; 6º ANO NOV: 18%; 6º ANO DEZ: 25% | PREVISTO | 75% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAR: 1e-06%; 6º ANO ABR: 0.5%; 6º ANO MAI: 2.5%; 6º ANO JUN: 1%; 6º ANO JUL: 6%; 6º ANO AGO: 10%; 6º ANO SET: 23%; 6º ANO OUT: 19%; 6º ANO NOV: 16%; 6º ANO DEZ: 17%; 6º ANO JAN: 0% | EXECUTADO | 75%
5.1.21. Recomposição de Talude em Gabião junto ao Córrego Santo Antônio no Contorno de Betim | Recomposição de Talude em Gabião junto ao Córrego Santo Antônio | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-05-20 | 2013-11-16 | 180 | 0% | PREVISTO | 6º ANO MAI: 10%; 6º ANO JUN: 14%; 6º ANO JUL: 1%; 6º ANO AGO: 5%; 6º ANO SET: 22%; 6º ANO OUT: 23%; 6º ANO NOV: 25% | PREVISTO | 70% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAI: 10%; 6º ANO JUN: 14%; 6º ANO JUL: 1%; 6º ANO AGO: 5%; 6º ANO SET: 35%; 6º ANO OUT: 19%; 6º ANO NOV: 16%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 70%
0%
|  |  | 0 | [46 empty] | 0%
5.2.2.1 Execução de Terceiras Faixas - 88 km | km 504+900 ao km 503+670 - Pista Norte - 1,23 km (correspondente ao km 504+900 ao km 503+700 - Pista Norte - 1,200 km) | 503.67 | 504.9 | APROVADO | NÃO SE APLICA | NÃO SE APLICA | 2013-11-01 | 2014-06-30 | 241 | 0% | PREVISTO | 6º ANO NOV: 2%; 6º ANO DEZ: 3%; 6º ANO JAN: 3%; 6º ANO FEV: 5%; 7º ANO MAR: 10%; 7º ANO ABR: 15%; 7º ANO MAI: 30%; 7º ANO JUN: 32% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 9%; 7º ANO MAR: 21%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 1%; 7º ANO JUL: 33%; 7º ANO AGO: 11%; 7º ANO SET: 24%; 7º ANO OUT: 0%; 7º ANO NOV: 1%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 506+020 ao km 504+930 - Pista Norte - 1,09 km (correspondente ao km 506+020 ao km 504+900 - Pista Norte - 1,120 km) | 504.93 | 506.02 | APROVADO | NÃO SE APLICA | NÃO SE APLICA | 2013-11-01 | 2014-06-30 | 241 | 0% | PREVISTO | 6º ANO NOV: 2%; 6º ANO DEZ: 3%; 6º ANO JAN: 3%; 6º ANO FEV: 5%; 7º ANO MAR: 10%; 7º ANO ABR: 15%; 7º ANO MAI: 30%; 7º ANO JUN: 32% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 8%; 7º ANO MAR: 10%; 7º ANO ABR: 0%; 7º ANO MAI: 3%; 7º ANO JUN: 6%; 7º ANO JUL: 33%; 7º ANO AGO: 9%; 7º ANO SET: 30%; 7º ANO OUT: 1%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 513+900 ao km 521+155 PS - 7,255 km | 513.9 | 521.155 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-08-01 | 2015-07-28 | 361 | 0% | PREVISTO | 7º ANO AGO: 0%; 7º ANO SET: 3%; 7º ANO OUT: 3%; 7º ANO NOV: 5%; 7º ANO DEZ: 10%; 7º ANO JAN: 12%; 7º ANO FEV: 12%; 7º ANO MAR: 12%; 7º ANO ABR: 15%; 7º ANO MAI: 14%; 7º ANO JUN: 12%; 7º ANO JUL: 2% | PREVISTO | 45% | ADIANTADA | 59%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 17%; 7º ANO OUT: 7%; 7º ANO NOV: 2%; 7º ANO DEZ: 5%; 7º ANO JAN: 13%; 7º ANO FEV: 15% | EXECUTADO | 59%
| km 520+200 ao km 525+200 - Pista Norte - 5,0 km (correspondente ao km 520+200 ao km 525+800 - Pista Norte - 5,600 km) | 520.2 | 525.2 | APROVADO | LICENCIADA | NÃO SE APLICA | 2015-01-15 | 2015-10-28 | 286 | 0% | PREVISTO | 7º ANO JAN: 0%; 7º ANO FEV: 3%; 7º ANO MAR: 3%; 7º ANO ABR: 5%; 7º ANO MAI: 10%; 7º ANO JUN: 15%; 7º ANO JUL: 18%; 7º ANO AGO: 18%; 7º ANO SET: 26%; 7º ANO OUT: 2% | PREVISTO | 3% | ADIANTADA | 14%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 14% | EXECUTADO | 14%
| km 527+795 ao km 528+760 PN - 0,965 km | 527.795 | 528.76 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-06-14 | 2013-12-11 | 180 | 0% | PREVISTO | 6º ANO JUN: 33%; 6º ANO JUL: 15%; 6º ANO AGO: 2%; 6º ANO SET: 4%; 6º ANO OUT: 12%; 6º ANO NOV: 15%; 6º ANO DEZ: 19% | PREVISTO | 50% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUN: 33%; 6º ANO JUL: 15%; 6º ANO AGO: 2%; 6º ANO SET: 10%; 6º ANO OUT: 32%; 6º ANO NOV: 5%; 6º ANO DEZ: 1%; 6º ANO JAN: 2%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 50%
| km 539+500 ao km 541+770 PS - 2,27 km | 539.5 | 541.77 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-06-14 | 2014-01-10 | 210 | 0% | PREVISTO | 6º ANO JUN: 6%; 6º ANO JUL: 17%; 6º ANO AGO: 7%; 6º ANO SET: 8%; 6º ANO OUT: 10%; 6º ANO NOV: 13%; 6º ANO DEZ: 17%; 6º ANO JAN: 22% | PREVISTO | 70% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUN: 6%; 6º ANO JUL: 17%; 6º ANO AGO: 7%; 6º ANO SET: 12%; 6º ANO OUT: 2%; 6º ANO NOV: 3%; 6º ANO DEZ: 2%; 6º ANO JAN: 11%; 6º ANO FEV: 6%; 7º ANO MAR: 13%; 7º ANO ABR: 15%; 7º ANO MAI: 5%; 7º ANO JUN: 0%; 7º ANO JUL: 1%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 70%
| km 555+710 ao km 561+398 PN - 5,688 km | 555.71 | 561.398 | APROVADO | LICENCIADA | NÃO SE APLICA | 2015-01-15 | 2015-11-28 | 317 | 0% | PREVISTO | 7º ANO JAN: 0%; 7º ANO FEV: 3%; 7º ANO MAR: 3%; 7º ANO ABR: 5%; 7º ANO MAI: 10%; 7º ANO JUN: 11%; 7º ANO JUL: 11%; 7º ANO AGO: 12%; 7º ANO SET: 22%; 7º ANO OUT: 21%; 7º ANO NOV: 2% | PREVISTO | 3% | ADIANTADA | 30%
[11 empty] | EXECUTADO | 6º ANO NOV: 0%; 6º ANO DEZ: 0%; 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 30% | EXECUTADO | 30%
| km 620+770 ao km 622+900 - Pista Sul - 2,130 km | 620.77 | 622.9 | APROVADO | NÃO SE APLICA | NÃO SE APLICA | 2014-02-01 | 2014-07-31 | 180 | 0% | PREVISTO | 6º ANO FEV: 20%; 7º ANO MAR: 16%; 7º ANO ABR: 20%; 7º ANO MAI: 18%; 7º ANO JUN: 16%; 7º ANO JUL: 10% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 18%; 7º ANO MAI: 9%; 7º ANO JUN: 8%; 7º ANO JUL: 21%; 7º ANO AGO: 22%; 7º ANO SET: 11%; 7º ANO OUT: 9%; 7º ANO NOV: 2%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 699+100 ao km 701+000 - Pista Norte - 1,900 km | 699.1 | 701 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-03-01 | 2014-09-30 | 213 | 0% | PREVISTO | 7º ANO MAR: 0%; 7º ANO ABR: 16%; 7º ANO MAI: 20%; 7º ANO JUN: 18%; 7º ANO JUL: 16%; 7º ANO AGO: 10%; 7º ANO SET: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 5%; 7º ANO JUN: 0%; 7º ANO JUL: 4%; 7º ANO AGO: 5%; 7º ANO SET: 20%; 7º ANO OUT: 27%; 7º ANO NOV: 35%; 7º ANO DEZ: 4%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 809+610 ao km 811+330 - Pista Sul - 1,72 km (correspondente ao km 809+700 ao km 810+800 - Pista Sul - 1,100 km) | 809.61 | 811.33 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-04-30 | 180 | 0% | PREVISTO | 6º ANO NOV: 10%; 6º ANO DEZ: 16%; 6º ANO JAN: 20%; 6º ANO FEV: 20%; 7º ANO MAR: 20%; 7º ANO ABR: 14% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 0%; 6º ANO OUT: 30%; 6º ANO NOV: 19%; 6º ANO DEZ: 12%; 6º ANO JAN: 23%; 6º ANO FEV: 16%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 837+390 ao km 838+590 - Pista Norte - 1,200 km | 837.39 | 838.59 | APROVADO | NÃO SE APLICA | NÃO SE APLICA | 2014-02-01 | 2014-07-31 | 180 | 0% | PREVISTO | 6º ANO FEV: 20%; 7º ANO MAR: 16%; 7º ANO ABR: 20%; 7º ANO MAI: 18%; 7º ANO JUN: 16%; 7º ANO JUL: 10% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 23%; 7º ANO MAI: 8%; 7º ANO JUN: 22%; 7º ANO JUL: 29%; 7º ANO AGO: 16%; 7º ANO SET: 2%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 866+600 ao km 865+480 - Pista Norte - 1,12 km (correspondente ao km 866+560 ao km 865+920 - Pista Norte - 0,640 km) | 865.48 | 866.6 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-04-30 | 180 | 0% | PREVISTO | 6º ANO NOV: 10%; 6º ANO DEZ: 16%; 6º ANO JAN: 20%; 6º ANO FEV: 20%; 7º ANO MAR: 20%; 7º ANO ABR: 14% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 42%; 6º ANO DEZ: 2%; 6º ANO JAN: 16%; 6º ANO FEV: 7%; 7º ANO MAR: 33%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 878+650 ao km 880+360 - Pista Sul - 1,71 km (correspondente ao km 878+600 ao km 880+000 - Pista Sul - 1,400 km) | 878.65 | 880.36 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-04-30 | 180 | 0% | PREVISTO | 6º ANO NOV: 10%; 6º ANO DEZ: 16%; 6º ANO JAN: 20%; 6º ANO FEV: 20%; 7º ANO MAR: 20%; 7º ANO ABR: 14% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 10%; 6º ANO DEZ: 0%; 6º ANO JAN: 13%; 6º ANO FEV: 7%; 7º ANO MAR: 15%; 7º ANO ABR: 28%; 7º ANO MAI: 24%; 7º ANO JUN: 3%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 909+960 ao km 908+510 - Pista Norte - 1,45 km (correspondente ao km 909+740 ao km 908+840 - Pista Norte - 0,900 km) | 908.51 | 909.96 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-04-30 | 180 | 0% | PREVISTO | 6º ANO NOV: 10%; 6º ANO DEZ: 16%; 6º ANO JAN: 20%; 6º ANO FEV: 20%; 7º ANO MAR: 20%; 7º ANO ABR: 14% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 9%; 6º ANO DEZ: 1%; 6º ANO JAN: 0%; 6º ANO FEV: 7%; 7º ANO MAR: 30%; 7º ANO ABR: 16%; 7º ANO MAI: 6%; 7º ANO JUN: 13%; 7º ANO JUL: 15%; 7º ANO AGO: 3%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 923+050 ao km 919+500 - Pista Norte - 3,550 km | 919.5 | 923.05 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-08-01 | 2015-02-28 | 211 | 0% | PREVISTO | 7º ANO AGO: 9%; 7º ANO SET: 16%; 7º ANO OUT: 20%; 7º ANO NOV: 18%; 7º ANO DEZ: 16%; 7º ANO JAN: 10%; 7º ANO FEV: 11% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 9%; 7º ANO SET: 6%; 7º ANO OUT: 22%; 7º ANO NOV: 17%; 7º ANO DEZ: 12%; 7º ANO JAN: 30%; 7º ANO FEV: 4% | EXECUTADO | 100%
| km 927+470 ao km 925+990 - Pista Norte - 1,48 km (correspondente ao km 927+470 ao km 926+340 - Pista Norte - 1,130 km) | 925.99 | 927.47 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-11-01 | 2014-04-30 | 180 | 0% | PREVISTO | 6º ANO NOV: 10%; 6º ANO DEZ: 16%; 6º ANO JAN: 20%; 6º ANO FEV: 20%; 7º ANO MAR: 20%; 7º ANO ABR: 14% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO NOV: 14%; 6º ANO DEZ: 17%; 6º ANO JAN: 7%; 6º ANO FEV: 17%; 7º ANO MAR: 11%; 7º ANO ABR: 34%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 933+720 ao km 935+150 - Pista Sul - 1,430 km | 933.72 | 935.15 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-08-01 | 2015-02-28 | 211 | 0% | PREVISTO | 7º ANO AGO: 9%; 7º ANO SET: 16%; 7º ANO OUT: 20%; 7º ANO NOV: 18%; 7º ANO DEZ: 16%; 7º ANO JAN: 10%; 7º ANO FEV: 11% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 9%; 7º ANO SET: 12%; 7º ANO OUT: 18%; 7º ANO NOV: 19%; 7º ANO DEZ: 40%; 7º ANO JAN: 2%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 944+560 ao km 945+410 - Pista Sul - 0,850 km | 944.56 | 945.41 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-08-01 | 2015-02-28 | 211 | 0% | PREVISTO | 7º ANO AGO: 11%; 7º ANO SET: 16%; 7º ANO OUT: 20%; 7º ANO NOV: 18%; 7º ANO DEZ: 16%; 7º ANO JAN: 10%; 7º ANO FEV: 9% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 11%; 7º ANO SET: 28%; 7º ANO OUT: 21%; 7º ANO NOV: 29%; 7º ANO DEZ: 11%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 947+910 ao km 946+990 - Pista Norte - 0,920 km | 946.99 | 947.91 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-08-01 | 2015-02-28 | 211 | 0% | PREVISTO | 7º ANO AGO: 0%; 7º ANO SET: 16%; 7º ANO OUT: 20%; 7º ANO NOV: 18%; 7º ANO DEZ: 16%; 7º ANO JAN: 10%; 7º ANO FEV: 20% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 34%; 7º ANO DEZ: 55%; 7º ANO JAN: 11%; 7º ANO FEV: 0% | EXECUTADO | 100%
| km 41+000 ao km 49+000 PN - 8 km | 41 | 49 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-11-01 | 2015-04-28 | 178 | 0% | PREVISTO | 7º ANO NOV: 4%; 7º ANO DEZ: 8%; 7º ANO JAN: 20%; 7º ANO FEV: 22%; 7º ANO MAR: 22%; 7º ANO ABR: 24% | PREVISTO | 54% | ADIANTADA | 55%
[11 empty] | EXECUTADO | 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 14%; 7º ANO DEZ: 8%; 7º ANO JAN: 12%; 7º ANO FEV: 21% | EXECUTADO | 55%
| km 41+000 ao km 49+000 PS - 8 km | 41 | 49 | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-11-01 | 2015-04-28 | 178 | 0% | PREVISTO | 7º ANO NOV: 4%; 7º ANO DEZ: 8%; 7º ANO JAN: 20%; 7º ANO FEV: 22%; 7º ANO MAR: 22%; 7º ANO ABR: 24% | PREVISTO | 54% | ADIANTADA | 55%
[11 empty] | EXECUTADO | 6º ANO JAN: 0%; 6º ANO FEV: 0%; 7º ANO MAR: 0%; 7º ANO ABR: 0%; 7º ANO MAI: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 14%; 7º ANO DEZ: 8%; 7º ANO JAN: 12%; 7º ANO FEV: 21% | EXECUTADO | 55%
| km 50+248 ao km 51+691 PS - 1,443 km | 50.248 | 51.691 | APROVADO | LICENCIADA | NÃO SE APLICA | 2013-06-14 | 2013-12-14 | 183 | 0% | PREVISTO | 6º ANO JUN: 1%; 6º ANO JUL: 10%; 6º ANO AGO: 10%; 6º ANO SET: 12%; 6º ANO OUT: 18%; 6º ANO NOV: 22%; 6º ANO DEZ: 27% | PREVISTO | 79% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUN: 1%; 6º ANO JUL: 10%; 6º ANO AGO: 10%; 6º ANO SET: 8%; 6º ANO OUT: 8%; 6º ANO NOV: 21%; 6º ANO DEZ: 39%; 6º ANO JAN: 3% | EXECUTADO | 79%
| km 477 ao 490 PN e PS - 26 km | 477 | 490 | APROVADO | LICENCIADA | NÃO SE APLICA | 2015-01-15 | 2016-01-30 | 380 | 0% | PREVISTO | 7º ANO JAN: 0%; 7º ANO FEV: 4%; 7º ANO MAR: 6%; 7º ANO ABR: 5%; 7º ANO MAI: 6%; 7º ANO JUN: 5%; 7º ANO JUL: 10%; 7º ANO AGO: 7%; 7º ANO SET: 10%; 7º ANO OUT: 13%; 7º ANO NOV: 15%; 7º ANO DEZ: 16%; 7º ANO JAN: 3% | PREVISTO | 4% | ADIANTADA | 5%
[11 empty] | EXECUTADO | [37 empty] | EXECUTADO | 5% | bar: 7º ANO ABR to 7º ANO FEV
5.3 COMPLEMENTAÇÃO DE OBRAS DO DNIT | km 15+800 - Bacci - Passagem Superior | - | - | APROVADO | LICENCIADA | PUBLICADO (23/04/2014) | 2013-09-01 | 2014-10-30 | 424 | 0% | PREVISTO | 6º ANO AGO: 5%; 6º ANO SET: 0%; 6º ANO OUT: 0%; 6º ANO NOV: 3%; 6º ANO DEZ: 5%; 6º ANO FEV: 4%; 7º ANO MAR: 4%; 7º ANO ABR: 7%; 7º ANO MAI: 7%; 7º ANO JUN: 7%; 7º ANO JUL: 9%; 7º ANO AGO: 14%; 7º ANO SET: 16%; 7º ANO OUT: 19% | PREVISTO | 95% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO AGO: 5%; 6º ANO SET: 19%; 6º ANO OUT: 18%; 6º ANO NOV: 6%; 6º ANO DEZ: 2%; 6º ANO JAN: 8%; 6º ANO FEV: 25%; 7º ANO MAR: 10%; 7º ANO ABR: 6%; 7º ANO MAI: 1%; 7º ANO JUN: 0% | EXECUTADO | 95%
| km 25+800 - Esmeralda - Passagem Inferior | - | - | APROVADO | LICENCIADA | PUBLICADO (23/04/2014) | 2013-11-01 | 2014-10-30 | 363 | 0% | PREVISTO | 6º ANO NOV: 3%; 6º ANO DEZ: 6%; 6º ANO FEV: 7%; 7º ANO MAR: 5%; 7º ANO ABR: 6%; 7º ANO MAI: 7%; 7º ANO JUN: 7%; 7º ANO JUL: 10%; 7º ANO AGO: 14%; 7º ANO SET: 16%; 7º ANO OUT: 19% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO SET: 12%; 6º ANO OUT: 7%; 6º ANO NOV: 5%; 6º ANO DEZ: 4%; 6º ANO JAN: 15%; 6º ANO FEV: 30%; 7º ANO MAR: 22%; 7º ANO ABR: 2%; 7º ANO MAI: 3%; 7º ANO JUN: 0% | EXECUTADO | 100%
| km 32+850 - São Sebastião - Passagem Inferior | - | - | APROVADO | LICENCIADA | PUBLICADO (23/04/2014) | 2013-11-01 | 2014-11-30 | 394 | 0% | PREVISTO | 6º ANO NOV: 2%; 6º ANO DEZ: 5%; 6º ANO FEV: 5%; 7º ANO MAR: 5%; 7º ANO ABR: 6%; 7º ANO MAI: 7%; 7º ANO JUN: 7%; 7º ANO JUL: 9%; 7º ANO AGO: 10%; 7º ANO SET: 13%; 7º ANO OUT: 15%; 7º ANO NOV: 16% | PREVISTO | 100% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO OUT: 7%; 6º ANO NOV: 5%; 6º ANO DEZ: 2%; 6º ANO JAN: 0%; 6º ANO FEV: 5%; 7º ANO MAR: 27%; 7º ANO ABR: 5%; 7º ANO MAI: 10%; 7º ANO JUN: 14%; 7º ANO JUL: 9%; 7º ANO AGO: 10%; 7º ANO SET: 6% | EXECUTADO | 100%
| km 12+200 - Guaripocaba II | - | - | APROVADO | LICENCIADA | NÃO SE APLICA | 2014-04-01 | 2015-02-28 | 333 | 0% | PREVISTO | 6º ANO JUL: 8%; 6º ANO AGO: 2%; 7º ANO ABR: 5%; 7º ANO MAI: 5%; 7º ANO JUN: 5%; 7º ANO JUL: 5%; 7º ANO AGO: 6%; 7º ANO SET: 7%; 7º ANO OUT: 6%; 7º ANO NOV: 8%; 7º ANO DEZ: 13%; 7º ANO JAN: 15%; 7º ANO FEV: 15% | PREVISTO | 90% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO JUL: 8%; 6º ANO AGO: 2%; 6º ANO SET: 31%; 6º ANO OUT: 50%; 6º ANO NOV: 8%; 6º ANO DEZ: 1%; 6º ANO JAN: 0%; 6º ANO FEV: 0% | EXECUTADO | 90%
6.5.1. SISTEMA DE PESAGEM - Implantação de Edificação - Balança Fixa | km 58+000 - Mairiporã/SP - Pista Norte - Fixa | - | - | EM ANÁLISE NA ANTT | AGUARDANDO ÓRGÃO AMBIENTAL | PUBLICADO (03/12/2013) | 2015-03-01 | 2016-03-28 | 393 | 0% | PREVISTO | 7º ANO MAR: 2%; 7º ANO ABR: 5%; 7º ANO MAI: 6%; 7º ANO JUN: 7%; 7º ANO JUL: 8%; 7º ANO AGO: 8%; 7º ANO SET: 9%; 7º ANO OUT: 9%; 7º ANO NOV: 10%; 7º ANO DEZ: 10%; 7º ANO JAN: 9%; 7º ANO FEV: 9%; 7º ANO MAR: 8% | PREVISTO | 0% | OBRA A INICIAR | 0%
[11 empty] | EXECUTADO | [37 empty] | EXECUTADO | 0% | bar: 6º ANO JAN to 7º ANO FEV
| km 58+000 - Mairiporã/SP - Pista Sul - Fixa | - | - | EM ANÁLISE NA ANTT | AGUARDANDO ÓRGÃO AMBIENTAL | PUBLICADO (03/12/2013) | 2015-03-01 | 2016-03-28 | 393 | 0% | PREVISTO | 7º ANO MAR: 2%; 7º ANO ABR: 5%; 7º ANO MAI: 6%; 7º ANO JUN: 7%; 7º ANO JUL: 8%; 7º ANO AGO: 8%; 7º ANO SET: 9%; 7º ANO OUT: 9%; 7º ANO NOV: 10%; 7º ANO DEZ: 10%; 7º ANO JAN: 9%; 7º ANO FEV: 9%; 7º ANO MAR: 8% | PREVISTO | 0% | OBRA A INICIAR | 0%
[11 empty] | EXECUTADO | [37 empty] | EXECUTADO | 0% | bar: 6º ANO JAN to 7º ANO FEV
| km 515+100 - Igarapé/MG - Pista Norte - Fixa | - | - | EM ANÁLISE NA ANTT | LICENCIADA | PUBLICADO | 2015-03-01 | 2016-03-28 | 393 | 0% | PREVISTO | 7º ANO MAR: 2%; 7º ANO ABR: 5%; 7º ANO MAI: 6%; 7º ANO JUN: 7%; 7º ANO JUL: 8%; 7º ANO AGO: 8%; 7º ANO SET: 9%; 7º ANO OUT: 9%; 7º ANO NOV: 10%; 7º ANO DEZ: 10%; 7º ANO JAN: 9%; 7º ANO FEV: 9%; 7º ANO MAR: 8% | PREVISTO | 0% | OBRA A INICIAR | 0%
[11 empty] | EXECUTADO | [37 empty] | EXECUTADO | 0% | bar: 7º ANO ABR to 7º ANO FEV
| km 515+200 - Igarapé/MG - Pista Sul - Fixa | - | - | EM ANÁLISE NA ANTT | LICENCIADA | PUBLICADO (23/04/2014) | 2015-03-01 | 2016-03-28 | 393 | 0% | PREVISTO | 7º ANO MAR: 2%; 7º ANO ABR: 5%; 7º ANO MAI: 6%; 7º ANO JUN: 7%; 7º ANO JUL: 8%; 7º ANO AGO: 8%; 7º ANO SET: 9%; 7º ANO OUT: 9%; 7º ANO NOV: 10%; 7º ANO DEZ: 10%; 7º ANO JAN: 9%; 7º ANO FEV: 9%; 7º ANO MAR: 8% | PREVISTO | 0% | OBRA A INICIAR | 0%
[11 empty] | EXECUTADO | [37 empty] | EXECUTADO | 0% | bar: 7º ANO ABR to 7º ANO FEV
6.3. ITS E EQUIPAMENTOS | Sistema de Detecção de Altura | - | - | EM ELABORAÇÃO | NÃO SE APLICA | NÃO SE APLICA | 2015-10-01 | 2015-12-28 | 88 | 0% | PREVISTO | 7º ANO OUT: 32%; 7º ANO NOV: 34%; 7º ANO DEZ: 34% | PREVISTO | 0% | OBRA A INICIAR | 0%
[11 empty] | EXECUTADO | [37 empty] | EXECUTADO | 0% | bar: 6º ANO JAN to 6º ANO FEV; 7º ANO DEZ to 7º ANO FEV
| Implantação e Instalação dos Equipamentos e Sistemas - Balança Fixa | - | - | EM ELABORAÇÃO | NÃO SE APLICA | NÃO SE APLICA | 2015-10-01 | 2015-12-28 | 88 | 0% | PREVISTO | 7º ANO OUT: 32%; 7º ANO NOV: 34%; 7º ANO DEZ: 34% | PREVISTO | 0% | OBRA A INICIAR | 0%
[11 empty] | EXECUTADO | [37 empty] | EXECUTADO | 0% | bar: 6º ANO JAN to 6º ANO FEV; 7º ANO DEZ to 7º ANO FEV
| Sistema de Controle de Velocidade (Radar) | - | - | APROVADO | NÃO SE APLICA | NÃO SE APLICA | 2013-05-01 | 2014-02-28 | 303 | 0% | PREVISTO | 6º ANO MAI: 6%; 6º ANO JUN: 9%; 6º ANO JUL: 7%; 6º ANO AGO: 2%; 6º ANO SET: 2%; 6º ANO OUT: 10%; 6º ANO NOV: 12%; 6º ANO DEZ: 15%; 6º ANO JAN: 17%; 6º ANO FEV: 20% | PREVISTO | 76% | CONCLUÍDA | 100%
[11 empty] | EXECUTADO | 6º ANO MAI: 6%; 6º ANO JUN: 9%; 6º ANO JUL: 7%; 6º ANO AGO: 2%; 6º ANO SET: 2%; 6º ANO OUT: 40%; 6º ANO NOV: 18%; 6º ANO DEZ: 4%; 6º ANO JAN: 0%; 6º ANO FEV: 12%; 7º ANO ABR: 0%; 7º ANO JUN: 0%; 7º ANO JUL: 0%; 7º ANO AGO: 0%; 7º ANO SET: 0%; 7º ANO OUT: 0%; 7º ANO NOV: 0%; 7º ANO DEZ: 0%; 7º ANO JAN: 0%; 7º ANO FEV: 0% | EXECUTADO | 76%

## PLANO DE AÇÃO (hidden)
PLANOS DE AÇÃO
ITEM PER | DESCRIÇÃO | UN. | QUANT. | KM INICIAL | KM FINAL | PREVISÃO PER |  | SITUAÇÃO DA OBRA | RESTRIÇÃO (DETALHAR, se necessário por meio de relatório) / MOTIVOS DE ATRASO | RELATÓRIO - Restrição / motivos de atraso
[6 empty] | INÍCIO | TÉRMINO
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! |  |  |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!